## Gantt
项目说明： 1）项目组成员严格按照工作安排开展工作，项目进展按每2周总结并提交周报；（由寇珑璇汇总，并上传 ,目录地址：info&data/weeklyReport,文件名称格式 "智慧钻井项目周报-2020/3/13-2020/3/27"） 2）项目研究过程中，产生的非密文档、代码等定时上传到GitHub（https://github.com/CSUDUC/intellDrilling），方便大家共享、交流学习，涉密数据勿上传（如原始数据）： 方法1上传目录RNN(LSTMetc) 方法2上传目录Statistics(ARMAetc) 方法3上传目录HTM 方法介绍见目录内ReadMe 3）项目开展过程中，遇到问题请及时在群里沟通，以免耽误工作进程； 4）每2周会根据项目组成员工作进展情况，发布下周工作安排。 |  | 项目名称 | 乐东10-1气田超高温高压井井下复杂情况预测模型研究 | [6 empty] | Legend:
|  | 工程信息中心 | [7 empty] | On Track |  |  |  |  | Low Risk |  |  |  |  | Med Risk |  |  |  |  | High Risk |  |  |  |  | Unassigned
[5 empty] | Project Start Date: |  | 2020-03-13
|  | 项目组成员 | 刘云飞、周壮、赵子飞、寇珑璇、熊邵潘、郭威龙 |  | Scrolling Increment: |  | 0 |  |  | March | [20 empty] | April | [27 empty] | May
 | time axis 2020-03-13 to 2020-05-07
| This row contains headers for the project schedule that follows below them. Navigate from B7 through BL7 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I7 and continues through cell BL7. All project timeline charting is auto generated based on the category, start date and number of days entered in the Milestones table. | Milestone Description | Notes | Category | Assigned To | Progress | Start | end | No. Days | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
| Enter Project information starting in cell B9 through cell G9. Sample data is in cells B9 through G33. Enter Milestone Description, select a Category from the drop-down list, assign someone to the item, enter the progress, start date and number of days for the task to start charting. The next instruction is in cell A34. | 1、预测方法研究
|  | 1）基于时间序列监测参数自学习变化预测与自适应阈值调整的事故预测算法的设计与实现 | LSTM+阈值自适应调整 | High Risk | 刘云飞+郭威龙 | 0% | 2020-03-13 | 2020-04-11 | 30
|  | 开展各类事故前、后各监测参数变化特性分析，确定各类事故预测相关参数 |  | Med Risk |  | 0% | 2020-03-13 | 2020-03-19 | 7
|  | 研究设计特征优选等关键特征提取算法，剔除冗余信息，构建事故预测关键特征因子，强化特征对各类事故的表征能力 |  | On Track |  | 0% | 2020-03-20 | 2020-03-29 | 10
|  | 2周工作总结 |  | High Risk |  | 0% | 2020-03-27 | 2020-03-27 | 1
……
|  | 2）基于时间窗口监测参数滑动自回归与监督学习的事故预测 | ARM等统计学习方法 | High Risk | 周壮+寇珑璇 | 0% | 2020-03-13 | 2020-04-11 | 30
|  | 开展各类事故前、后各监测参数变化特性分析，确定各类事故预测相关参数 |  | Med Risk |  | 0% | 2020-03-13 | 2020-03-19 | 7
|  | 研究设计特征优选等关键特征提取算法，剔除冗余信息，构建事故预测关键特征因子，强化特征对各类事故的表征能力 |  | On Track |  | 0% | 2020-03-20 | 2020-03-29 | 10
|  | 2周工作总结 |  | High Risk |  | 0% | 2020-03-27 | 2020-03-27 | 1
……
|  | 3）基于时间序列监测参数内在模式关系学习与异常检测的事故预测 | HTM方法 | High Risk | 赵子飞+熊邵潘 | 0% | 2020-03-13 | 2020-04-11 | 30
|  | 开展各类事故前、后各监测参数变化特性分析，确定各类事故预测相关参数 |  | Med Risk |  | 0% | 2020-03-13 | 2020-03-19 | 7
|  | 研究设计特征优选等关键特征提取算法，剔除冗余信息，构建事故预测关键特征因子，强化特征对各类事故的表征能力 |  | On Track |  | 0% | 2020-03-20 | 2020-03-29 | 10
|  | 2周工作总结 |  | High Risk |  | 0% | 2020-03-27 | 2020-03-27 | 1
|  | …… |  | Med Risk |  | 0% | 2019-10-25 |  | 3
|  |  |  | Med Risk |  | 0% | 2019-10-28 |  | 4
|  |  |  | Med Risk |  | 0% | 2019-11-01 |  | 3
|  |  |  | High Risk |  | 0% | 2019-10-13 |  | 5
|  |  |  | Milestone |  | 0% | 2019-10-18 |  | 2
|  |  |  | Low Risk |  | 0% | 2019-11-04 |  | 5
|  |  |  | Goal |  | 0% | 2019-11-09 |  | 4
|  |  |  | Goal |  | 0% | 2019-11-13 |  | 1
|  |  |  | Goal |  | 0% | 2019-11-14 |  | 2
|  |  |  | Goal |  | 0% | 2019-11-16 |  | 2
|  |  |  | Goal |  | 0% | 2019-11-18 |  | 2
|  |  |  | High Risk |  | 0% | 2019-10-18 |  | 2
|  |  |  | Med Risk |  | 0% | 2019-10-20 |  | 1
|  |  |  | High Risk |  | 0% | 2019-10-13 |  | 8
|  |  |  | High Risk |  | 0% | 2019-10-21 |  | 8
|  | Task 5 |  | Milestone
Title 4
Task 1
Task 2
|  | Task 3 |  | Milestone
Task 4
Task 5
This is an empty row
| This row marks the end of the Gantt milestone data. DO NOT enter anything in this row. To add more items, insert new rows above this one. | To add more data, Insert new rows ABOVE this one

## About
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks description, select a category of Goal, Milestone, On Track, Low Risk, Med Risk, High Risk, Progress as a percent of task completion, a Start Date and Number of days to complete the task. The Gantt chart fills in and is color coded to help distinguish the various categories. A scroll bar allows you to scroll through the timeline. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. Gantt Chart About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. This hidden text will not print. To remove these instructions from the worksheet, simply delete column A.
This is the last instruction in this worksheet.